## Sheet1
Republic of the Philippines
Province of Davao del Norte
CITY OF TAGUM
INDIVIDUAL PROGRAM OF WORK
(For All Types of Project)
[9 empty] | Date: | 2024-09-10
Name/ Location of Project |  |  |  | Approriation: |  |  |  | 7800000
|  |  |  | Source of Funds: |  |  |  | DBP LOAN 2023
COMPLETION OF SCHOOL BUILDINGS
(3-Units CL @ 2nd Floor, 3-Units CL @ 3rd Floor with Roofing) |  |  |  | Calendar Days to Complete: |  |  |  | 198 Working Days
|  |  |  | Desirable Starting Date: |  |  |  | UPON DELIVERY OF MATERIALS
RIZAL ELEMENTARY SCHOOL, BRGY. MAGUGPO SOUTH, TAGUM CITY |  |  |  | Mode of Implementation: | ADMINISTRATION |  |  | ADMINISTRATION
Project Category: |  |  |  | Project Description:
[8 empty] | 8m x 9m | area per classroom
|  |  |  | No. of Units @ |  |  | 2nd Floor | 3 | CL
Vertical Structure | [6 empty] | 3rd Floor | 3 | CL
Minimum Equipment Requirement: |  |  |  | Manpower Requirement:
| 1-Bagger Mixer, Dumptruck, Bar Cutter, Bar Bender |  |  |  |  | Project Engineer, Mason, Carpenter, Welder, Tinsmith,
| Angle Grinder, Drilling Tool, Welding Machine, Minor Tools |  |  |  |  | Painter, Skilled Worker, Laborer/Helper
ESTIMATED DIRECT COST
Item | Description | % of |  | Quantity |  |  | Units | Unit Cost | Total
No. |  | Total | [6 empty] | Cost
B.5 | Project Billboard / Signboard | 0.02853% |  | 1 |  |  | LS | 2022 |  | 2022
801 | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | 0.2393% |  | 1 |  |  | LS | 16960 |  | 16960
803 | STRUCTURE EXCAVATION | 0% |  | 0 |  |  | cu.m. | #DIV/0! |  | 0
804 | EMBANKMENT | 0% |  | 0 |  |  | cu.m. | #DIV/0! |  | 0
PART B. | PLAIN AND REINFORCED CONCRETE WORK
900 | REINFORCED CONCRETE | 26.38% |  | 75.3435 |  |  | cu.m. | 24810.1694 |  | 1869285
903 | FORMWORKS & FALSEWORKS | 15.72% |  | 1 |  |  | LS | 1114322.5 |  | 1114322.5
PART C. | FINISHINGS AND OTHER CIVIL WORKS
1046 | MASONRY WORKS | 3.186% |  | 349.44 |  |  | sq.m. | 646.2368 |  | 225821
1027 | CEMENT PLASTER FINISH/DECORATIVE STONE | 1.821% |  | 720.72 |  |  | sq.m. | 179.0598 |  | 129052
1021 | CEMENT FLOOR FINISH | 0% |  | 0 |  |  | sq.m. | #DIV/0! |  | 0
1003 | CARPENTRY AND JOINERY WORKS | 10.25% |  | 360.96 |  |  | sq.m. | 2012.0096 |  | 726255
1010 | WOODEN DOORS AND WINDOWS | 3.725% |  | 12 |  |  | set/s | 22000.3333 |  | 264004
1047 | METAL STRUCTURES | 19.92% |  | 16917.786 |  |  | kg/s | 83.4533 |  | 1411845
1014 | PREPAINTED METAL SHEETS | 6.838% |  | 312.32 |  |  | sq.m. | 1551.6489 |  | 484611
1001 | STORM DRAINAGE AND SEWERAGE SYSTEM | 0.3071% |  | 1 |  |  | L.S. | 21767 |  | 21767
1002 | PLUMBING WORKS | 0% |  | 1 |  |  | LS | 0 |  | 0
1018 | CERAMIC/GRANITE TILES | 1.447% |  | 96 |  |  | sq.m. | 1068.5417 |  | 102580
1032 | PAINTING, VARNISHING AND OTHER RELATED WORKS | 5.282% |  | 1723.4503 |  |  | sq.m. | 217.2166 |  | 374362
1008 | ALUMINUM GLASS WINDOWS | 0% |  | 1 |  |  | L.S. | 0 |  | 0
1012 | GLASS AND GLAZING | 0% |  | 1 |  |  | L.S. | 0 |  | 0
1039 | ALUMINUM COMPOSITE PANEL WORKS | 0% |  | 1 |  |  | L.S. | 0 |  | 0
1004 | HARDWARE | 0% |  | 1 |  |  | L.S. | 0 |  | 0
PART D. | ELECTRICAL
1100 | CONDUITS, BOXES & FITTINGS (CONDUIT WORKS/ CONDUIT ROUGH-IN) | 0.6198% |  | 1 |  |  | LS | 43928 |  | 43928
1101 | WIRES AND WIRING DEVICES | 1.849% |  | 1 |  |  | LS | 131064 |  | 131064
1102 | POWER LOAD CENTER, SWITCHGEAR AND PANELBOARDS, AND OTHER OVER CURRENT PROTECTION DEVICES | 0.5511% |  | 1 |  |  | LS | 39057 |  | 39057
1103 | LIGHTING FIXTURES AND LAMPS | 1.839% |  | 1 |  |  | LS | 130310 |  | 130310
PART E. | MECHANICAL
1200 | AIR CONDITIONING AND VENTILATING SYSTEM | 0% |  | 1 |  |  | LS | 0 |  | 0
Total |  | 100% | [6 empty] | P | 7087245.5
Breakdown of Estimated Direct Cost: |  |  |  | Indirect Cost
| Description | Total Cost |  | 1. OVERHEAD EXPENSES (5% of Direct Cost) |  |  |  |  | P | 354362.275
1 | Materials | P | 5109176.5 | 1.1 ADMINISTRATIVE COST (2% of Direct Cost) | [5 empty] | 141744.91
2 | Labor | P | 1978069 | 1.2 PRE-ENGINEERING - POWER BILL DEPOSIT, PEE Professional Fee, ICT, Office Supplies (2% of Direct Cost) | [5 empty] | 141744.91
3 | Equipment Rental | P |  | 1.3 OFFICE EXPENSES - POWER CONSUMPTION (1% of Direct Cost) | [5 empty] | 70872.455
4 | POL | P |  | 2. CONTINGENCY (3.56% of Direct Cost) |  |  |  |  | P | 252083.5375
5 | RROW | P |  | 3. MISCELLANEOUS EXPENSES (0.5% of Direct Cost) |  |  |  |  | P | 35436.2275
6 | Overhead/Misc. | P |  | 4. PERMITS, CLEARANCES & OTHER GOV'T TAXES (1% of Direct Cost) |  |  |  |  | P | 70872.46
7 | SUPPLY & APPLICATION | P | 0
| Total | P | 7087245.5 |  |  |  | Total |  | P | 712754.5
[7 empty] | Direct & Indirect Cost |  |  | 7800000
Prepared by : |  | Checked by: | [7 empty] | 7800000
[7 empty] | PROJECT COST |  | P | 7800000
| SHEILA M. JUANILLO, CE | LIMWELL A. FLORES, CE, RMP, Mat'ls Engr. 1
| Engineer II | Engineer III, SS
| EDWIN L. MELCHOR | CARLOS I. FERIDO, REE
| Engineering Assistant | Engineer III, VES
Reviewed by: |  | Recommended by : |  |  |  |  | Approved by:
| ROMEO C. VILLARENTE JR. | ERIC F. CLEMENTE |  |  |  |  | REY T. UY
| Architect, Tax Mapper IV | Acting City Architect |  |  |  |  | City Mayor